{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["예정공정표"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"예정공정표","index":0,"n_rows":46,"n_cols":36,"rows_kept":46,"cut":false,"hidden":false,"merged":[[45,0,45,35],[5,0,5,1],[6,0,6,1],[37,35,38,35],[13,35,14,35],[5,31,5,34],[7,35,8,35],[9,35,10,35],[15,0,16,0],[15,35,16,35],[17,35,18,35],[19,35,20,35],[11,0,12,0],[13,0,14,0],[29,35,30,35],[31,0,32,0],[0,0,0,35],[5,35,6,35],[7,0,8,0],[9,0,10,0],[5,2,5,30],[43,0,44,0],[17,0,18,0],[19,0,20,0],[21,0,22,0],[23,0,24,0],[33,0,34,0],[37,0,38,0],[35,0,36,0],[39,0,40,0],[25,0,26,0],[27,0,28,0],[29,0,30,0]]}
["아주대 생활관 구내인터넷 시설 구축공사 예정 공정표(안)"]
[]
[]
["공사명 : 2016년 아주대 생활관 구내인터넷(장비 대개체,철거 포함)구축 공사"]
[]
["                           일 정",null,"9월",{"$nulls":28},"10월",null,null,null,"비고"]
["공 정 별",null,"2일","3일","4일","5일","6일","7일","8일","9일","10일","11일","12일","13일","14일","15일","16일","17일","18일","19일","20일","21일","22일","23일","24일","25일","26일","27일","28일","29일","30일","1일","2일","3일","4일"]
["1. 자재,물자준비 및 공사협의 ","계획"]
[null,"실행"]
["2. 화홍관 철거 및 설치","계획"]
[null,"실행"]
["    - 1F~3F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 4F~5F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 화홍관 시험 및 보완작업","계획"]
[null,"실행"]
["3. 남제관 철거 및 설치","계획",{"$nulls":33},"명절 연휴로 공사 일시 중단"]
[null,"실행"]
["    - 1F~2F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 3F~4F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 남제관 시험 및 보완작업","계획"]
[null,"실행"]
["4. 광교관 철거 및 설치","계획"]
[null,"실행"]
["    - 1F~3F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 4F~5F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 광교관 시험 및 보완작업","계획"]
[null,"실행"]
["5. 용지관 철거 및 설치","계획"]
[null,"실행"]
["    - 1F~3F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 4F~5F 철거 및 설치작업","계획"]
[null,"실행"]
["    - 용지관 시험 및 보완작업","계획"]
[null,"실행"]
["6. 최종 시험 및 정리정돈 작업","계획"]
["     (기존 장비 철거)","실행"]
["7. 절체후 장애대비 현장대기","계획"]
[null,"실행"]
["※ 설치시 공정률에 따라 일정이 변경될 수 있습니다"]